## STLC
# | STLC(PTLC) Stage Name | Notes | Activities/Tasks | Deliverables
1 | Requirement Analysis |  | 1. Identify performance criteria (e.g., SLA, response time, throughput) 2. Analyze use cases and workload models | 1. Performance Test Requirements Document 2. Workload model
2 | Test Planning | Tool Selection Test design | 1. Define test objectives, scope, and strategy 2. Select tools and hardware requirements 3. Create risk assessment 4. Schedule resources and timelines | Performance Test Plan (Test Tool Configuration Plan, Risk Assessment report, Test schedule)
3 | Test Case Development | Test script development | 1. Develop test scripts for scenarios (e.g., load, stress, endurance) 2. Prepare test data | 1. Performance Test Scripts 2. Test Data
4 | Environment Setup |  | 1. Configure a production-like environment for performance testing 2. Set up tools, servers, databases, and network 3. Validate the setup with a dry run | 1. Configured Test Environment
5 | Test Execution | Monitoring & Analysis Tuning and Optimization Retesting Reporting | 1. Execute performance tests (load, stress, spike, endurance, etc.) 2. Monitor system metrics during test runs 3. Identify and log defects, retest | 1. Test Execution Logs 2. Monitoring Metrics 3. Defect Logs
6 | Test Cycle Closure | Final Reporting | 1. Analyze test results and compare with requirements 2. Identify bottlenecks and recommend optimizations 3. Document lessons learned | 1. Test Closure Report ( Test analysis summary/statistics, recommendations)